## Gantt Chart
GANTT CHART
PROJECT TITLE |  | WEBTECH |  |  |  |  | COMPANY NAME | [6 empty] | Mainframemasters
PROJECT MANAGER |  | Joshua Pearson |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1 | Project Conception and Initiation | Joshua P. | 2024-03-08 | 2024-05-15 | 2 | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 5 M to WEEK 5 T
1.1 | Project Scope Definition | Joshua P. | 2024-03-08 | 2024-05-15 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 5 M to WEEK 5 T
1.2 | Technology Stack Selection | Kabir S. | 2024-03-08 | 2024-05-15 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W; WEEK 5 M to WEEK 5 T
2 | Project Definition and Planning
2.1 | Database Schema Design | Kabir S. | 2024-03-18 | 2024-05-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 R; WEEK 5 M to WEEK 5 T
2.2 | Database Implementation | Kabir S. | 2024-03-18 | 2024-05-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 5 F
3 | Backend Development
3.1 | API Endpoint Design | Kabir S. | 2024-03-18 | 2024-05-15 | 2 | 100% | bar: WEEK 1 W to WEEK 1 F; WEEK 2 W to WEEK 2 F; WEEK 5 M to WEEK 5 T
3.2 | API Development | Kabir S. | 2024-03-18 | 2024-05-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 5 M to WEEK 5 T
4 | Frontend Development
4.1 | UI/UX Design | Josiah B. | 2024-03-18 | 2024-05-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 6 M to WEEK 7 M
4.2 | Homepage Development | Josiah B. | 2024-03-18 | 2024-05-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 T to WEEK 5 T
4.3 | Product Page Development | Josiah B. | 2024-03-18 | 2024-05-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 T to WEEK 5 T
4.4 | Other Pages Development | Josiah B. | 2024-03-18 | 2024-05-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 T to WEEK 5 T; WEEK 7 F to WEEK 10 F
5 | Testing and QA | All | 2024-03-18 | 2024-05-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 7 F to WEEK 10 F
6 | Deployment and Launch | Joshua P. | 2024-03-18 | 2024-05-15 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 7 F to WEEK 10 F
7 | Post-Launch and Maintenance | All | 2024-03-18 | 2024-05-15 |  | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 5 M to WEEK 5 T